| Delivery Date | Project Month | Work Package | Output | Responsibility |
| --- | --- | --- | --- | --- |
| 28th /29th October 2004 | 1 | 2 | Workshop 1 Consider blueprint for ESEC. | Action by All. ONS to host in London. |
| 30th November 2004 | 2 | 2 | Report on prototype ESEC inc. derivation Matrices. | UESSEX-ISER |
| 28th February 2005 | 5 | 3 | Web based statistical compendium. | Warwick with UESSEX-ISER |
| 30th/31st March 2005 | 6 | 1 | Workshop 2 Revisions to ESEC and final plans for validation studies. |

Action by all.  Host?

| Location? |
| --- |
| 31st March 2005 | 6 | 1 | First six monthly project report to Commission. | ONS |
| 29th April 2005 | 7 | 4 | Report: evaluation of the ESEC prototype, revisions to matrices and validation plans. | Warwick, UESSEX-ISER , ONS |
| 30th September 2005 | 8 to 13 | 5 to 11 | Individual validation studies draft reports for peer review. | UESSEX-SER, UNMANN_MZES, INSEE, ErasmusMC, SOFI, UNINIB, ESRI |
| 30th September 2005 | 12 | 1 | Second six monthly project report to Commission. | ONS |
| 31st October 2005 | 13 | 5 to 11 | All final Validation Study reports delivered to ONS. | UESSEX-SER, UNMANN_MZES, INSEE, ErasmusMC, SOFI, UNINIB, ESRI |

3rd October 2005 to

| 21st July 2006 | 13 to 22 | 14 | Assist participant current and future member states to apply the prototype ESEC to their own national statistical sources. | WARWICK |
| --- | --- | --- | --- | --- |
| 1st November 2005 to 20th January 2006 | 16 | 12 | Review validation studies and refine prototype ESEC. Prepare report for project conference in January 2006. | ONS, UESSEX-ISER, WARWICK |
| 26th /27th January 2006 | 16 | 12 | Project conference. Consortium + Eurostat. NSIs and academics to review and revise applications and validation of the ESEC prototype. |

Host ? Location?

| Action by all. |
| --- |
| 2nd February 2006 | 17 | 12 | Final version of ESEC on project website. | UESSEX-ISER |
| 31st March 2006 | 18 | 1 | Third six monthly project report to Commission. | ONS |
| 2nd February 2006 to 31st May 2006 | 17 to 20 | 13 |

Develop an operational guide to the ESEC.

|  | ONS, with UESSEX-ISER, WARWICK plus consortium's advice. |
| --- | --- |
| 31st May 2006 | 20 | 13 | Operational guide, as web based resource in place. | ONS, with UESSEX-ISER, WARWICK |
| 27th/28th July 2006 | 22 | 14 | Workshop 4. for current and future EU member states. | Host? Location? WARWICK leads on package. |
| 29th September 2006 | 24 | 14 | Report. Applications and recommendations for ESEC in current and future EU countries. | WARWICK |
| 2nd October 2006 | 24 | 1 | Final project report to Commission. | ONS |

ESEC Workshops/conferences *

| Workshops | Date | Location | Host | Project month |
| --- | --- | --- | --- | --- |
| 1. to consider blueprint. | 28/29 October 2004 | London | ONS | 1. |
| 2. Revisions to prototype ESEC. | 30/31 March 2005 | ?? | ?? | 6 |
| 3. Project conference. Consortium + Eurostat, NSIs and academics to review and revise applications and validation of the ESEC prototype. | 26/27 January 2006 | ?? | ?? | 16 |
| 4. Workshop for current and future EU member states. | 27/28 July 2006 | ?? | ?? | 22 |

*Note. We have scheduled four workshops for the consortium partners but two of these will be expanded into conferences, which will involve a wider group of participants.

We expect each workshop /conference to run over two days.  The conferences will include a half day or full day for consortium business.

ESEC Project

Co-ordinators' Proposals For Project Delivery Dates

ESEC Workshop 1

ONS London

28/29 October 2004