European Commission Sixth Framework Programme

Citizens and Governance in a Knowledge based Society

Development of a European Socio-economic Classification (ESeC)

Project Co-ordination Committee – Second Consortium Meeting, INSEE, Paris, Room 539, Fifth Floor, 18 Boulevard Adolphe Pinard, March 30-31, 2005

Agenda Item 7: Timetable to Naples and Beyond

The following is the timetable leading to the Naples (I hope!) conference.

It is vital that we all meet the deadlines set out here.

2005

April 15	Final validation plans (c. 750-1000 words, plus 100-150 word summary) to Essex, copied to Warwick and ONS

April 29	Report by UK partners on the evaluation of the ESeC prototypes, the resulting derivation matrices and the validation plans

April 29	Derivation matrices sent by Essex to all partners

May-Sept	Validation studies

September 30	Draft reports on validation studies to Essex. These will be circulated to all consortium members for comments. Member’s comments to be sent to Essex by for collation and circulation. (Submission of reports by September 15 would be even better!)

Associated draft work package reports to ONS.

October-

July 2006	Warwick to liaise with NSIs leading to July Workshop

October 15-21	Comments on validation studies to be sent out by Essex to all consortium members

October 31	Final validation reports and associated work package reports to ONS, copied to Essex and Warwick

November 1 -

December 15	Preparation of reports as papers for the Naples conference

December 1	Draft agenda for Naples conference

December 15	Final date for submission of validation papers for Naples conference

2006

January 15	Evaluation report by UK partners of validation studies and any recommendations for changes to ESeC, plus papers and agenda for Naples

January 25-27	Naples conference (dates to be confirmed)

February 	Final version of ESeC

February-

September	Essex produces user manual (by end of May) and edits Naples conference papers into a book

July (end)	Workshop for NSIs – venue and dates to be decided